## Sprint 3 Deliverables
Task | # hours (expected) | # hours (Actual) | Contributer(s) | Status
Attachment model | 3 | 5 | Jackson B | Complete
(front end) edit/add-project fuctionality | 3 | 3.5 | Thomas H | Complete
Sponsor Workflow | 5 | 6 | Thomas H, Cole M, Gates A | Complete
Interface Design | 4 | 6 | Cole M, Gates A | Complete
Student Oauth Through My Bama | 5 | 2 | Cole K | Reassigned to after otka migration
Sponsor 2FA | 1 | NA | Cole K | In Progress
Student Email Verification | 2 | NA | Cole K | In Progress
Student Assignment Page | 3 | 3 | Cole M | Complete
Student Submission Deadline Logic | 0.5 | 0.5 | Cole M | Complete
Add semester model | 2 | 2 | Jackson B | Complete
Add feedback model | 2 | 2 | Jackson B | Complete
Require authentication for DRF endpoints | 3 | 1 | Jackson B | Complete
Add workflow and actions for Admin | 6 | 10 | Jackson B, Gates | Complete
Add Admin action for updating the status of multiple projects | 1 | 1 | Jackson B | Complete
Delete the actual file when deleting attachments | 3 | 3 | Jackson B | Will not be completed
Frontend file attachment functionality | 3 |  |  | Will not be completed
Dynamic rank form requirements | 2 |  |  | Will not be completed
Pinia stores for Sponsor workflow | 2 |  |  | Will not be completed
Sponsor assigned student view | 1 |  |  | Will not be completed